## Sheet1
Task | Estimated Time | Self-Assign | Target Deadline | Actual Time | Actual Delivery | Status (IP/C) | Comments | Kenan Review | Charlie Review | Qianyi Review | Louise Review
MODEL
Minimal Student Class | 10 min | Kenan | 03/23/24 | 1 hr | 03/23/24 | C |  | C |  |  | C
Minimal Lecture Class | 10 min | Kenan | 03/23/24 | 30 min | 03/23/24 | C |  | C |  |  | C
Minimal Course Class | 10 min | Louise | 03/23/24 | 30 min | 03/24/24 | C |  | C |  |  | C
Minimal Professor Class | 10 min | Qianyi | 03/23/24 | 10 min | 03/24/24 | C |  | C |  |  | C
Minimal AttendanceRecord Class | 15 min | Qianyi | 03/23/24 | 15 min | 03/24/24 | C |  | C |  |  | C
Minimal AttendanceSession Class | 10 min | Qianyi | 03/23/24 | 10 min | 03/24/24 | C |  | C |  |  | C
Minimal PersistanceManager Class | 30 min | Louise | 03/23/24 | 20 min | 03/24/24 | C |  | C |  |  | C
Minimal Notifier Interface | 15 min | Charlie | 03/23/24 | 30 min | 03/24/24 | IP |  | C
Minimal EmailNotifier Class | 15 min | Charlie | 03/23/24 | 30 min | 03/24/24 | IP |  | C
University Class | 5 min | Louise | 03/27/24 | 5 min | 03/27/24 | C |  | C |  |  | C
ProtectedInfo Class | 5 min | Louise | 03/27/24 | 5 min | 03/27/24 | C |  | C |  |  | C
VIEW
UI for Student Display | 30 min | Kenan | 03/24/24 | 30 min | 03/24/24 | C |  | C |  |  | C
UI for Student Status | 30 min | Charlie | 03/24/24 | 30 min | 03/25/24 | C |  | C |  |  | C
UI for Lecture Display | 30 min | Kenan | 03/24/24 | 15 min | 03/25/24 | C |  | C |  |  | C
UI for Course Display | 30 min | Charlie | 03/25/24 | 10 min | 03/25/24 | C |  | C |  |  | C
CONTROLLER
Loading Students From CSV | 30 min | Louise | 03/27/24 | 1 hour | 03/27/24 | C |  | C |  |  | C
Professor Register | 10 min | Louise | 03/27/24 | 10 min | 03/27/24 | C |  | C |  |  | C
Professor Login | 10 min | Louise | 03/27/24 | 10 min | 03/27/24 | C |  | C |  |  | C
update Students' Attendance Record | 30 min | Louise | 03/27/24 | 30 min | 03/27/24 | C |  | C |  |  | C
ask to load student' status for one lecture and a Course | 20 min | Louise | 03/27/24 | 20 min | 03/27/24 | C |  | C |  |  | C
Change Student Display Name | 30 min | Louise | 03/27/24 | 30 min | 03/27/24 | C |  | C |  |  | C
EXTRA
CI/CD | 2 hours | Charlie | 03/24/24 | 5 hours | 03/27/24 | C |  | C
TESTING
Loading Students From CSV | 1 hour | Louise | 03/27/24 | 1 hour | 03/27/24 | C |  | C |  |  | C
Professor Register |  |  | 03/27/24 |  | 03/27/24
Professor Login | 30 min | Kenan | 03/27/24 | 30 min | 03/27/24 | C
update Students' Attendance Record |  |  | 03/27/24 |  | 03/27/24
ask to load student' status for one lecture and a Course |  |  | 03/27/24 |  | 03/27/24
changeStudentDisplayName |  |  | 03/27/24 |  | 03/27/24
App Class |  |  | 03/27/24 |  | 03/27/24
EventManager Class |  |  | 03/27/24 |  | 03/27/24
Lecture Class |  | All | 03/27/24 |  | 03/27/24
PersistenceManager Class | 30 min | Kenan | 03/27/24 | 45 min | 03/27/24 | C |  | C
AttendanceSession + AttendanceRecord Classes | 1 hour | Kenan | 03/27/24 | 1.5 hours | 03/27/24 | C |  | C
Course Class | 15 min | Kenan | 03/27/24 | 30 min | 03/27/24 | C |  | C
Professor Class | 15 min | Kenan | 03/27/24 | 30 min | 03/27/24 | C |  | C
Student Class |  |  | 03/27/24 |  | 03/27/24
TextUserController Class |  | Louise | 03/27/24 |  | 03/27/24
TextUserView Class |  | All | 03/27/24 |  | 03/27/24
University Class |  |  | 03/27/24 |  | 03/27/24

## Sheet2
Task
Client | Professor Class
Register Class
LoginRequest Class
Shared | Course Class
Lecture Class
Student Class
AttendanceRecord Class
AttendanceSession Class
Server | PersistenceManager Class
Notifier Interface
EmailNotifier Class
UserAuthentication Class