## Evolution 1
Task | Estimated Time | Self-Assign | Target Deadline | Actual Time | Actual Delivery | Status (IP/C) | Comments | Kenan Review | Charlie Review | Qianyi Review | Louise Review
MODEL
Minimal Student Class | 10 min | Kenan | 03/23/24 | 1 hr | 03/23/24 | C |  | C |  |  | C
Minimal Lecture Class | 10 min | Kenan | 03/23/24 | 30 min | 03/23/24 | C |  | C |  |  | C
Minimal Course Class | 10 min | Louise | 03/23/24 | 30 min | 03/24/24 | C |  | C |  |  | C
Minimal Professor Class | 10 min | Qianyi | 03/23/24 | 10 min | 03/24/24 | C |  | C |  |  | C
Minimal AttendanceRecord Class | 15 min | Qianyi | 03/23/24 | 15 min | 03/24/24 | C |  | C |  |  | C
Minimal AttendanceSession Class | 10 min | Qianyi | 03/23/24 | 10 min | 03/24/24 | C |  | C |  |  | C
Minimal PersistanceManager Class | 30 min | Louise | 03/23/24 | 20 min | 03/24/24 | C |  | C |  |  | C
Minimal Notifier Interface | 15 min | Charlie | 03/23/24 | 30 min | 03/24/24 | IP |  | C
Minimal EmailNotifier Class | 15 min | Charlie | 03/23/24 | 30 min | 03/24/24 | IP |  | C
University Class | 5 min | Louise | 03/27/24 | 5 min | 03/27/24 | C |  | C |  |  | C
ProtectedInfo Class | 5 min | Louise | 03/27/24 | 5 min | 03/27/24 | C |  | C |  |  | C
VIEW
UI for Student Display | 30 min | Kenan | 03/24/24 | 30 min | 03/24/24 | C |  | C |  |  | C
UI for Student Status | 30 min | Charlie | 03/24/24 | 30 min | 03/25/24 | C |  | C |  |  | C
UI for Lecture Display | 30 min | Kenan | 03/24/24 | 15 min | 03/25/24 | C |  | C |  |  | C
UI for Course Display | 30 min | Charlie | 03/25/24 | 10 min | 03/25/24 | C |  | C |  |  | C
CONTROLLER
Loading Students From CSV | 30 min | Louise | 03/27/24 | 1 hour | 03/27/24 | C |  | C |  |  | C
Professor Register | 10 min | Louise | 03/27/24 | 10 min | 03/27/24 | C |  | C |  |  | C
Professor Login | 10 min | Louise | 03/27/24 | 10 min | 03/27/24 | C |  | C |  |  | C
update Students' Attendance Record | 30 min | Louise | 03/27/24 | 30 min | 03/27/24 | C |  | C |  |  | C
ask to load student' status for one lecture and a Course | 20 min | Louise | 03/27/24 | 20 min | 03/27/24 | C |  | C |  |  | C
Change Student Display Name | 30 min | Louise | 03/27/24 | 30 min | 03/27/24 | C |  | C |  |  | C
EXTRA
CI/CD | 2 hours | Charlie | 03/24/24 | 5 hours | 03/27/24 | C |  | C
TESTING
Loading Students From CSV | 1 hour | Louise | 03/27/24 | 1 hour | 03/27/24 | C |  | C |  |  | C
Professor Register |  |  | 03/27/24 |  | 03/27/24
Professor Login | 30 min | Kenan | 03/27/24 | 30 min | 03/27/24 | C
update Students' Attendance Record |  |  | 03/27/24 |  | 03/27/24
ask to load student' status for one lecture and a Course |  |  | 03/27/24 |  | 03/27/24
changeStudentDisplayName |  |  | 03/27/24 |  | 03/27/24
App Class |  |  | 03/27/24 |  | 03/27/24
EventManager Class |  |  | 03/27/24 |  | 03/27/24
Lecture Class |  | All | 03/27/24 |  | 03/27/24
PersistenceManager Class | 30 min | Kenan | 03/27/24 | 45 min | 03/27/24 | C |  | C
AttendanceSession + AttendanceRecord Classes | 1 hour | Kenan | 03/27/24 | 1.5 hours | 03/27/24 | C |  | C
Course Class | 15 min | Kenan | 03/27/24 | 30 min | 03/27/24 | C |  | C
Professor Class | 15 min | Kenan | 03/27/24 | 30 min | 03/27/24 | C |  | C
Student Class |  |  | 03/27/24 |  | 03/27/24
TextUserController Class |  | Louise | 03/27/24 |  | 03/27/24
TextUserView Class |  | All | 03/27/24 |  | 03/27/24
University Class |  |  | 03/27/24 |  | 03/27/24

## Evolution 2
| Task | [5 empty] | Sub-Program | Responsibility | Time | Status | Function | Class | Notes | we may change the ArrayList<Course> from class Professor to ArrayList<Section> so that section info can be stored. Section class can include Course and Int number, String ID as arrtibutes
Shared | Professor Class | [5 empty] | Client | Qianyi & Louise | 4/8-4/11 | Faculty & Student | logIn | TextUserController | receive id and passwords -> send to server -> check whether correct on server side with database -> return the result
| Section | [6 empty] | Qianyi & Louise | 4/8-4/11 | Faculty | loadProfessor |  | successfully log in -> request all required info from database and send a professor obj back
[8 empty] | Qianyi & Louise | 4/8-4/11 | Faculty | addNewCourse |  | load all courses from database -> add a course -> check whether currently teach this course -> if not add the course to this Professor obj -> send the Course info to the server and store in database
[8 empty] | Qianyi & Louise | 4/8-4/11 | Faculty | addSection | should be inside addNewCourse | select the course -> select the section -> send the data to server and database
Shared | Course Class | [6 empty] | Qianyi & Louise | 4/8-4/11 | Faculty | takeAttendance |  | select the course->select the section-> start new Lecture -> load students from database -> show students' name -> take attendance -> send the records to database
| Lecture Class | [6 empty] | Qianyi & Louise | 4/8-4/11 | Faculty | updateAttendance |  | select the course & section -> use course & section info to get all lectures by date from database -> show the lectures to users -> choose the exact lecture->get the attendance -> update the attendance -> send back to database
| Student Class | [6 empty] | Qianyi & Louise | 4/8-4/11 | Faculty | takeAttendanceFromPreviousDay |  | Not sure whether still need it if using updateAttendance
| AttendanceRecord Class | [6 empty] | Qianyi & Louise | 4/8-4/11 | Faculty | showReportForStudent |  | choose course & section -> get all students' records by the info (need to get the participation grade on server side)
| AttendanceSession Class | [6 empty] | Qianyi & Louise
Server | PersistenceManager Class | [6 empty] | Qianyi & Louise | [5 empty] | Student class may also need ArrayList<Section>
| Notifier Interface | [6 empty] | Qianyi & Louise | 4/8-4/11 | Student | loadStudent |  | log in -> request all required info from database and send a student obj back
| EmailNotifier Class | [6 empty] | Qianyi & Louise | 4/8-4/11 | Student | changeNotificationPreference |  | select Course -> show preference -> change or not -> if yes send to server and update the record
| UserAuthentication Class | [6 empty] | Qianyi & Louise | 4/8-4/11 | Student | getReportSummary |  | select Course -> get record with sectionID & calculate the participation points on server side -> send to client and show results
Qianyi & Louise
Database design | [7 empty] | Qianyi & Louise | 4/8-4/11 | Faculty & Student | App |  | integration, send socket and send specific command to run each function
| Student | ID | Name | Display Name | Email | University ID
| Instructor | ID | Name | Email | University ID
| Course | ID | Name |  |  |  | Server | Qianyi & Louise | 4/8-4/11 | plain server | checkMatch(id,password) |  | check id and password through database. send -1 to client if not match, 0 faculty, 1 student
| Section | ID | Course ID | Instructor ID | Name |  |  | Qianyi & Louise | 4/8-4/11 |  | logInHandler() |  | send a professor obj
| Lecture | ID | Section ID | Date |  |  |  | Qianyi & Louise | 4/8-4/11 |  | ClientHandler() |  | send a student obj
| Enrollment | Section ID | Student ID |  |  |  |  | Qianyi & Louise | 4/8-4/11 |  | allCoursesInDatabase |  | send a list of Courses in Database
| Attendance | ID | Lecture ID | Student ID | Status |  |  | Qianyi & Louise | 4/8-4/11 |  | allSectionsofCourse |  | send all sections of a Course in Database
| Passwords | User ID | Password | Status |  |  |  | Qianyi & Louise |  |  |  |  | let id be a faculty in SectionID
| University | ID | Name | ChangeName |  |  |  | Qianyi & Louise
| Notification | ID | Section ID | student ID | On/Off |  |  | Qianyi & Louise | 4/8-4/11 |  | getStudents(Section ID) |  | send list of students back
[8 empty] | Qianyi & Louise |  |  |  |  | no need to send anything?
| Student getStudent(String id) | [6 empty] | Qianyi & Louise | 4/8-4/11 |  | updateAttendance(LectureID,HashMap<student ID,AttendanceStatus>>) |  | set the info to database
[8 empty] | Qianyi & Louise | 4/8-4/11 |  | sendEmail(Student ID,Lecture ID) |  | get the courseID by lecture ID and check whether the Student ID's preference is on. If on, send the AttendaceRecord by Lecture ID
| AttendanceRecord getStudentStatus(Student student, Lecture lecture) | [6 empty] | Qianyi & Louise | 4/8-4/11 |  | getLectures(Section ID) |  | send a list of Lecture to client
| boolean checkPassword(String password, String ID) | [6 empty] | Qianyi & Louise | 4/8-4/11 |  | getAttendanceRecordsByLecture(Lecture ID) |  | send a list of records by lecture ID
[8 empty] | Qianyi & Louise | 4/8-4/11 |  | updateAttendance(Lecture ID,Student ID,AttendanceStatus) |  | change the attendanceStatus of student id by selecting exact lecture ID
[8 empty] | Qianyi & Louise | 4/8-4/11 |  | getStudentsRecords(Section ID) |  | get and send back a HashMap<Student, AttendanceRecordSummary>. AttendaceRecordSummay can be a new class includes arraylist of AttendanceRecord from one course and the score of the student
[8 empty] | Qianyi & Louise | 4/8-4/11 |  | calculateScore(ArrayList<AttendanceStatus>) |  | get a score for attendance of a student in one course
[8 empty] | Qianyi & Louise | 4/8-4/11 |  | updatePreference(Course ID,Student ID, boolean on) |  | change to turn on/off the notification by boolean on
[8 empty] | Qianyi & Louise | 4/8-4/11 |  | getAttendanceRecordSummaryForOne(Section ID,Student ID)
[8 empty] | Qianyi & Louise | 4/8-4/11 |  | getInfoFromDatabase(...) |  | get the CourseID, SectionID by Lecture ID
[8 empty] | Qianyi & Louise | 4/8-4/11 |  | IntegrationAttendanceRecordInfo(...) |  | one AttendanceRecord should include course name, student ID, Date,Status
[8 empty] | Charlie |  |  | DAOFunctions
[8 empty] | Qianyi & Louise | 4/8-4/11 |  | App |  | receive the socket, and choose different functions to run
[7 empty] | CourseManagement | Charlie |  | CourseManagement | addCourse(courseName,int sections) |  | assign a course ID for this course, create sections for this course in database
[8 empty] | Charlie |  |  | getSection(courseID) |  | get the number of sections in a Course
[8 empty] | Charlie |  |  | addSection(courseID) |  | add a new Section
[8 empty] | Charlie |  |  | enrollStudents(SectionID) |  | load students with below methods and put them to database
[8 empty] | Charlie |  |  | loadStudentsByCSV |  | return a list of students
[8 empty] | Charlie |  |  | loadStudentManually |  | return a student
[8 empty] | Charlie |  |  | removeSection(SectionID) |  | delete everything related with this Section
[8 empty] | Charlie |  |  | removeCourse(CourseID) |  | delete everything related with this Cours
[8 empty] | Charlie |  |  | updateCourseName(CourseID)
[8 empty] | Charlie |  |  | dropStudent(ID,SectionID)
[8 empty] | Charlie |  |  | CourseManagementTextView
[8 empty] | Charlie |  |  | What will update Class/Section DO???
Charlie
[8 empty] | Charlie |  |  | CourseManagementApp
[7 empty] | UserRegistration | Kenan | 4/5-4/11 | UserRegistration | addStudent(id, password) |  | register user
[8 empty] | Kenan | 4/5-4/11 |  | addProfessor(id,password)
[8 empty] | Kenan | 4/5-4/11 |  | removeUser(id) |  | delete user
[8 empty] | Kenan | 4/5-4/11 |  | updateUser(id,password) |  | change passwords
[8 empty] | Kenan | 4/5-4/11 |  | updatePasswords(id,newPassword)
[8 empty] | Kenan | 4/5-4/11 |  | UserRegistrationTextView |  | similar to E1 TextView
Kenan
Kenan
Kenan
[8 empty] | Kenan | 4/5-4/11 |  | UserRegistrationApp

## Evolution 3
Task | Member | Estimated Time | Finished Date | Actual Time
Admin GUI and debug from E2 | Kenan | 1 week | 2028-04-24 | 1 week
CourseManagement GUI and debug from E2 | Charlie | 1 week | 2028-04-24 | 1 week
Client Side GUI and Server Side Debug | Louise | 1 week | 2022-04-24 | 1 week
Extra Credit | Qianyi | 3 days | 2028-04-24 | 3 days
Admin Test Cases | Kenan | 1 week | 2028-04-24 | 1 week
CourseManagement Test Cases | Charlie | 1 day | 2029-04-24 | 1 day
Client Side and Server Side Test Cases | Louise | 3 days | 2028-04-24 | 3 days
Design Document | Everyone | 1 day | 2029-04-24 | 1 day
Case & User Mapping | Qianyi | 1 day | 2029-04-24 | 1 day
Class Diagram | Qianyi | 1 day | 2029-04-24 | 1 day
Specifc Function Requirements | Everyone | 1 day | 2029-04-24 | 1 day
Task Breakdown Sheet | Everyone | 1 day | 2029-04-24 | 1 day
Installation & Configuration Introduction | Louise | 1 day | 2029-04-24 | 1 day